## Slide 1
Post-Merger Integration Pack
Synergy tracking, Day 1 readiness, systems cutover, and owner actions.
Notes: Synthetic post-merger integration pack for real-corpus preservation evidence.

## Slide 2
Day 1 Readiness Tracker
Workstream | Owner | Status | Due | Risk
Finance close | Controller | Green | Day 1 | None
HR onboarding | People Ops | Yellow | Day 7 | Policy mapping
Customer comms | CX | Green | Day 3 | None
IT access | Security | Yellow | Day 5 | SSO exceptions
Legal entities | Legal | Green | Day 10 | Filings
Notes: Readiness table should preserve workstream owner and risk text.

## Slide 3
Synergy Capture Trend
Chart: 
| Month 1 | Month 2 | Month 3 | Month 4
Run-rate target | 1 | 2.5 | 4 | 6
Captured | 0.7 | 1.8 | 3.1 | 4.9
Notes: Synergy chart workbook and notes should survive round-trip.

## Slide 4
Systems Cutover Plan
System | Target | Dependency | Fallback
ERP | Month 2 | Chart mapping | Dual close
CRM | Month 1 | Account merge | Read-only archive
Data warehouse | Month 3 | Identity map | Batch replay
Support desk | Day 14 | Routing rules | Shared queue
Notes: Cutover table and connector should remain intact.

## Slide 5
Integration Owner Actions
Synergy model refresh
Finance
SSO exception cleanup
Security
Customer notice QA
CX
ERP cutover rehearsal
IT
Notes: Grouped integration action tiles should keep child text and transforms.

## Slide 6
Appendix: Integration Evidence Index
Artifact | Source | Owner
Synergy model | synergy_model.xlsx | Finance
Cutover tracker | systems_cutover.csv | IT
Customer comms | customer_notice.docx | CX
Access exceptions | sso_exceptions.csv | Security